## Baseline
project_id | project_name | wbs_level_1 | wbs_level_2 | wbs_level_3 | activity_id | discipline | activity_description | location | equipment_or_line_id | planned_start | planned_finish | planned_duration_days | predecessor_activity_id | successor_activity_id | planned_percent_complete | baseline_status | synthetic_data_flag
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Civil Works | Compressor Foundations / C21 | CIV-401 | Civil | Excavation for Compressor Foundation C21 | Compressor Area | C21 | 2026-10-01 | 2026-10-02 | 2 |  | CIV-402 | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Civil Works | Compressor Foundations / C21 | CIV-402 | Civil | PCC for Compressor Foundation C21 | Compressor Area | C21 | 2026-10-03 | 2026-10-03 | 1 | CIV-401 | CIV-403 | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Civil Works | Compressor Foundations / C21 | CIV-403 | Civil | Reinforcement fixing for Compressor Foundation C21 | Compressor Area | C21 | 2026-10-04 | 2026-10-05 | 2 | CIV-402 | CIV-404 | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Civil Works | Compressor Foundations / C21 | CIV-404 | Civil | Formwork for Compressor Foundation C21 | Compressor Area | C21 | 2026-10-06 | 2026-10-06 | 1 | CIV-403 | CIV-405 | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Civil Works | Compressor Foundations / C21 | CIV-405 | Civil | RCC concreting for Compressor Foundation C21 | Compressor Area | C21 | 2026-10-07 | 2026-10-07 | 1 | CIV-404 | ELE-607 | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Civil Works | Rack Foundations / Rack C | CIV-406 | Civil | Excavation for Rack C support foundations | Rack C | RC-FDN | 2026-10-03 | 2026-10-04 | 2 |  | CIV-407 | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Civil Works | Rack Foundations / Rack C | CIV-407 | Civil | RCC foundation work for Rack C supports | Rack C | RC-FDN | 2026-10-05 | 2026-10-07 | 3 | CIV-406 | PIP-502¦ELE-601 | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Civil Works | Cable Trenches / Substation Route | CIV-408 | Civil | Excavation for Substation cable trench S1 | Substation Area | S1 | 2026-10-05 | 2026-10-06 | 2 |  | ELE-604¦ELE-608 | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Civil Works | Utility Trenches / Tank Farm Route | CIV-409 | Civil | Excavation for utility trench TF-U1 | Tank Farm | TF-U1 | 2026-10-07 | 2026-10-08 | 2 |  | CIV-410¦PIP-507 | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Civil Works | Restoration / Project Area | CIV-410 | Civil | Final civil restoration around upgraded areas | Project Area | BETA-GEN | 2026-10-09 | 2026-10-10 | 2 | CIV-409 |  | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Piping Works | Compressor Suction / 20-C-501 | PIP-501 | Piping | Fabricate spools for Compressor Suction Line 20-C-501 | Fabrication Yard | 20-C-501 | 2026-10-03 | 2026-10-04 | 2 |  | PIP-503 | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Piping Works | Compressor Suction / 20-C-501 | PIP-502 | Piping | Install supports for Compressor Suction Line 20-C-501 | Rack C | 20-C-501 | 2026-10-08 | 2026-10-09 | 2 | CIV-407 | PIP-503 | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Piping Works | Compressor Suction / 20-C-501 | PIP-503 | Piping | Erect Compressor Suction Line 20-C-501 | Rack C | 20-C-501 | 2026-10-10 | 2026-10-12 | 3 | PIP-501¦PIP-502 | PIP-504 | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Piping Works | Compressor Suction / 20-C-501 | PIP-504 | Piping | Weld joints for Compressor Suction Line 20-C-501 | Rack C | 20-C-501 | 2026-10-13 | 2026-10-14 | 2 | PIP-503 | PIP-505 | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Piping Works | Compressor Suction / 20-C-501 | PIP-505 | Piping | Hydrotest Compressor Suction Line 20-C-501 | Rack C | 20-C-501 | 2026-10-15 | 2026-10-15 | 1 | PIP-504 |  | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Piping Works | Utility Line / 6-U-410 | PIP-506 | Piping | Fabricate spools for Utility Line 6-U-410 | Fabrication Yard | 6-U-410 | 2026-10-05 | 2026-10-06 | 2 |  | PIP-508 | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Piping Works | Utility Line / 6-U-410 | PIP-507 | Piping | Install supports for Utility Line 6-U-410 | Tank Farm | 6-U-410 | 2026-10-09 | 2026-10-10 | 2 | CIV-409 | PIP-508 | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Piping Works | Utility Line / 6-U-410 | PIP-508 | Piping | Erect Utility Line 6-U-410 | Tank Farm | 6-U-410 | 2026-10-11 | 2026-10-12 | 2 | PIP-506¦PIP-507 | PIP-509 | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Piping Works | Utility Line / 6-U-410 | PIP-509 | Piping | Weld and inspect joints for Utility Line 6-U-410 | Tank Farm | 6-U-410 | 2026-10-13 | 2026-10-14 | 2 | PIP-508 | PIP-510 | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Piping Works | Utility Line / 6-U-410 | PIP-510 | Piping | Hydrotest and reinstate Utility Line 6-U-410 | Tank Farm | 6-U-410 | 2026-10-15 | 2026-10-16 | 2 | PIP-509 |  | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Electrical Works | Cable Tray / Rack C | ELE-601 | Electrical | Install cable tray supports at Rack C | Rack C | TRAY-RC-SUP | 2026-10-08 | 2026-10-09 | 2 | CIV-407 | ELE-602 | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Electrical Works | Cable Tray / Rack C | ELE-602 | Electrical | Install cable trays at Rack C | Rack C | TRAY-RC | 2026-10-10 | 2026-10-11 | 2 | ELE-601 |  | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Electrical Works | Panels / Substation Area | ELE-603 | Electrical | Install feeder panel FP-02 | Substation Area | FP-02 | 2026-10-05 | 2026-10-06 | 2 |  |  | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Electrical Works | Power Cable / Compressor C-501 | ELE-604 | Electrical | Lay power cable from FP-02 to Compressor C-501 | Substation Area | PC-C501 | 2026-10-07 | 2026-10-09 | 3 | CIV-408 | ELE-605 | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Electrical Works | Power Cable / Compressor C-501 | ELE-605 | Electrical | Terminate power cable PC-C501 at FP-02 | Substation Area | PC-C501 | 2026-10-10 | 2026-10-10 | 1 | ELE-604 | ELE-606 | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Electrical Works | Power Cable / Compressor C-501 | ELE-606 | Electrical | Terminate power cable PC-C501 at Compressor C-501 | Compressor Area | PC-C501 | 2026-10-11 | 2026-10-11 | 1 | ELE-605 |  | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Electrical Works | Earthing / Compressor Area | ELE-607 | Electrical | Provide equipment earthing for Compressor C-501 | Compressor Area | C-501 | 2026-10-08 | 2026-10-08 | 1 | CIV-405 |  | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Electrical Works | Control Cable / Compressor C-501 | ELE-608 | Electrical | Lay control cable CC-C501 | Substation Area | CC-C501 | 2026-10-07 | 2026-10-08 | 2 | CIV-408 | ELE-609 | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Electrical Works | Control Cable / Compressor C-501 | ELE-609 | Electrical | Terminate and continuity-test control cable CC-C501 | Compressor Area | CC-C501 | 2026-10-09 | 2026-10-10 | 2 | ELE-608 | ELE-610 | 0 | NOT_STARTED | TRUE
BETA-001 | Project Beta — Compressor & Utility Upgrade | Project Beta — Compressor & Utility Upgrade | Electrical Works | Completion / Project Area | ELE-610 | Electrical | Final electrical inspection for upgraded systems | Project Area | ELE-BETA-CLOSE | 2026-10-11 | 2026-10-12 | 2 | ELE-609 |  | 0 | NOT_STARTED | TRUE